## Template project timeline
Project start date | 2024-10-01
Deadline to raise funds | 2024-10-21
Task | Assigned to | Start Date | Due Date | Status | Notes | Links to further resources
Planning | [5 empty] | Crowdfunding Guide
KEY TASK Host kick-off meeting with your group and society, assign project roles and agree timelines |  | 2024-10-03 | 2024-10-03 | Not started |  | (template) planning meeting agenda.pdf
KEY TASK Confirm project page open and close date |  | 2024-10-03 | 2024-10-03 | Not started | We recommend fundraising for no longer than two or three weeks, with 10 days being the ideal timeframe to actively fundraise
Share this completed plan with uob-crowdfunding@bristol.ac.uk |  | 2024-10-01 | 2024-10-04 | Not started
Creating your project pitch, video, and rewards | [5 empty] | Help writing your project pitch
Create itemized budget breakdown for project |  | 2024-10-05 | 2024-10-06 | Not started |  | Page 7, Crowdfunding Guide
Finalize minimum and maximum funding target |  | 2024-10-05 | 2024-10-06 | Not started | What's the minimum you need to go ahead, and how will you spend any additional funds if you are successful?
Collect photos for your pitch |  | 2024-10-05 | 2024-10-07 | Not started
Submit your project pitch for your webpage |  | 2024-10-05 | 2024-10-07 | Not started
Create plan for your crowdfunding video (messages, structure, location, individuals that will feature) |  | 2024-10-06 | 2024-10-09 | Not started |  | Page 8, Crowdfunding Guide
Arrange filming dates |  | 2024-10-05 | 2024-10-05 | Not started
KEY TASK Complete editing of your one-minute fundraising video |  | 2024-10-05 | 2024-10-08 | Not started
Finalize your project rewards, if offering them |  | 2024-10-05 | 2024-10-07 | Not started |  | Rewards Guide
Assign rewards donation amounts |  | 2024-10-05 | 2024-10-07 | Not started
Make any final amendments as suggested by Bristol Crowdfunding to your pitch |  | 2024-10-08 | 2024-10-10 | Not started
Making a promotional plan | [5 empty] | Promotional Guide
KEY TASK Assign campaign roles: Who will sign up to be a helper and make asks, who will lead on events, who will lead on press and corporate relationships |  | 2024-10-03 | 2024-10-03 | Not started
KEY TASK Map your audience and identify the channels you will use to contact them - who will be interested in supporting your project and why? |  | 2024-10-03 | 2024-10-05 | Not started |  | Page 10, Crowdfunding Guide
Create social media plan to help raise awareness around the campaign and accompany asks that individuals will make to their contacts |  | 2024-10-04 | 2024-10-05 | Not started
Idea generation for types of updates and content you will post about your project |  | 2024-10-03 | 2024-10-05 | Not started
KEY TASK Complete your promotional plan and submit this to Bristol Crowdfunding to review (mapping out who you will ask and when) |  | 2024-10-08 | 2024-10-10 | Not started |  | (template) promotional plan.xlsx
Project page goes live |  |  | 2024-10-10 | Not started
Collect photos and videos to use during the promotion of your project |  | 2024-10-03 | 2024-10-05 | Not started
Write emails and social media posts for launch |  | 2024-10-05 | 2024-10-11 | Not started |  | (template) - asking cheat sheet.pdf
Write emails and social media posts for mid-campaign |  | 2024-10-05 | 2024-10-13 | Not started
Write emails and social media posts for end of campaign |  | 2024-10-05 | 2024-10-16 | Not started
KEY TASK Project page closes to donations |  |  | 2024-10-21 | Not started
Thanking your supporters
Write final email and social media posts thanking supporters and letting them know when they will receive their rewards |  | 2024-10-21 | 2024-10-21 | Not started
Create and send rewards to your supporters |  | 2024-10-21 | 2024-10-31 | Not started | The sooner you do this, the better
Notify uob-crowdfunding@bristol.ac.uk that you've sent your rewards and thanked your supporters, ready for funds to be transferred |  | 2024-10-21 | 2024-11-02 | Not started
Send uob-crowdfunding@bristol.ac.uk a picture and short written update on your project once funds have been sent |  | 2024-10-21 | 2024-11-10 | Not started